## Meashured website
Step 1
Measured Website | Tech activities | Designs will be done by WSG, Pages and content will be Created by Design team. It is simple CMS site where a user will be provided to register on behalf of University | data will be stored at AWS postgress sql db(Common for Data Wrangler and Website)
Registration | Adding license
login | Create an instance using Lamda
forget password | payment gateway
NDA agreement | Email send
about us
how it works
FAQ
Purchase product

## Lamda
On successful Registration, Lamda will create a New instance for the University

## data wrangler
| User activities | Tech activities | Preparatory/background activities | Have the rules readymade as Generic, so that basic rules are applied readily by the end user. Also when user is entering new Rule, it should be named appropriately, to retrieve back the rule, system shoul provide option to change/switch the rules as per the need.
check login with product license and time period
| Select LMS and add required params for pulling the data | store the details and try to pull the data using either from api or db as the case may be | 1.Identify all the APIs to be Pulled for Each system.Note that only the endpoint and Token will be provided by the enduser. It is the system which pulls the data. |  | LMS | Canvas LMS/Blackboard/Moodle
| Select SIS and add required params for pulling the data | store the details and try to pull the data using either from api or db as the case may be | 2.Identify all the tables to be Pulled for Each system.Note that only the db details will be provided by the enduser. It is the system which pulls the data. |  | SIS | Campus Nexus
| Select CRM and add required params for pulling the data | store the details and try to pull the data using either from api or db as the case may be |  |  | CRM | Dynamic CRM
| check for the proper connection | using appropriate connectors connect and fetch top 10 rows and show it | make multiple connectors for db, like mysql, oracle, pgsql, ms sql, sql etc..
| set scheduler for pulling | connect with the system at given time and pull the data | Check for the CRON plugin within the system also make it part with timegap, otherwise we will be blacklisted.
| Receives the email regarding the first pull | send mail once the first pull is completed | Need to discuss how to store the pulled raw data.
| Option is provided IT admin for appling Rules | after the first pull the data will be audited | 1. Created a class for data audit.
| user selects the appropriate Bucket | User can apply generic rule , or he can create rules
| The table list will be shown | User can apply generic rule , or he can create rules
| First data audit will be carried out for each table | User can apply generic rule , or he can create rules
| Then the table level manipulation setting will be done | User can apply generic rule , or he can create rules
| Then column level manipulation will be done | User can apply generic rule , or he can create rules | generic or user provided rules will be applied to the data for preparation to ETL
| Add user roles | Store the data | pass on to ETL
| Add user groups | Store the data | pass on to ETL
| add User | store the data | pass on to ETL
Clarification needed
1 | How many rules will be effective at a given time for a university? If multiple rules are permitted then, For each rule, we need to send different set of same data.
2 | When ever new rule is applied, what to do with already pushed data?
3 | How to store the data of initial Pull? We have planned to break it into table and store in a file. Top folder --> Meta folder,Data Folder meta folder contains all the meta information like table name, column name data folder will contain all the data ina JSON format for each file.
4 | should we follow the same pattern for the Subsequent Pull also?
5 | If API s is provided we have to pull all the data, unless they are provided with Delta option.
6 | Also if API, then it is not possible to use all the apis at a go, we will be blacklisted. We should try to pull with a time gap.
7 | After setting up the RULEs, is this system process the data, or the Talend will process the data as per rule available? Else Which system will process which rule, as per talend, the Data transformation, convertion of Dates, Pivoting are already available with them.
8 | More items to come?

## KBCONFIG DB BREAKDOWN
I have tried to break the usage of tables as per different purposes within Data Wrangler, Please go through it, Lot of tables can be removed. We need your inputs.
University/College (website) | User(Under Univeristy) | Data Pulling | Data Audit | Data configuration | Supply to ETL | master | At Dashboard | To be decided
client | additionalrestrictions | clientsystemsetting | columndistinctvalues | custom | mashconfigconnectortype | appmaster | cachedinformation | adobeanalytics
clientconnectorlicense | group | clientsystemsettingintervals | columnobjecttype | customfielddatasettings | mashconfiguration | datepattern | linkedparameters | clientquestiontype
countries | previlegecategories | comparatorlevel | columnscommondistinctvalues | customfielddatasettings_backup | mashconfiguration_connectionsettings | metadatacolumns | pagemaster | customfielddetails_backup
license | role | connectionconfiguration | columnsimilaritystatistics | customfielddetails | mashconfigurationdistinctfilters | privileges | pageparamdetails | customfielddatasettings_backup1
| user | connectionsettings | dataattributetypes | customfielddetails_defaultvalues | mashconfigurationstatus | product | pagetabdetails | distinct_leads
| user_country_currency | connectortype | datatrainingvaluedetails | customtable | mashjoincolumn | roleprivileges | reportdateintervals | messagemaster
| userdefaultsettings | connectortypesetting | output-onlinetsvtools | displayablecolumns | mashjoincolumnpercentage | sys_datatypes | reports | questioncomments
| usergrouprolesetting | connectortypesource | primarytables | entitycomparison | mashjoincolumnpercentagedistribution | sys_models | reportwidgets | questionlikes
| userroleexception | dataaccessapiurls | statevariableconfiguration | formuladetails | mashnonrelationalconfigurationsetting | sys_objecttypes | reportdateintervals | questions
|  | filterablecolumns | statevariableorderinfo | mashjoinconfiguration | mashrelationalconfigurationsettings | tbllogcategories | tblconfigurationattributes | questionshare
|  | managecredential | statevariableordersettings | reverseindex | mashupconfigurationdataobjectsettings | tbllogmessages | tblconfigurationcalander | questiontypes
|  | systemsettingsdetails | statevariablesettings | reverseindexstatus | mashupdataobject | validationstatus | tblconfigurationcalander1
|  | tblapiconnectiondetailes | statevariablesyncpoint |  | mashupdatasecurity | validationtypes |  | tblgeniefeedback
|  | tblvirtualvariablevalue | statevariabletimelocation |  | mashupdatasecuritysettings | widget_data
|  | transformation | statevariabletimewindow |  | mashupdatastoreconnectionsettings
|  |  | virtualregexinfo |  | mashupdatastoreconnectortype |  | mandotoryfields
|  |  | virtuallookupinfo |  | mashupdatastoreconnectortypesetting
|  |  | virtualtableconfiguration |  | mashupdatesettings
|  |  | virtualtablesettings |  | mashupprivileges
|  |  | virtualvariablecolumns |  | mashupsearchpersonalization
|  |  | virtualvariableconfiguration |  | mashupsearchpersonalizationcolumns
mashupsecurity
mashupsecurityprivilages
sys_mashsettingattributes
sys_metrictypes
validationconfiguration

## User
User(Under Univeristy)
additionalrestrictions | group | previlegecategories | role | user | user_country_currency | userdefaultsettings | usergrouprolesetting | userroleexception
| GroupID |  |  | UserId
| GroupName |  |  | LoginId
| ClientID |  |  | UserName
| CreateDateTime |  |  | LoginPassword
| LastChangeDateTime |  |  | ActiveDirectory
| CreateUserId |  |  | DomainName
| LastChangeUserId |  |  | ClientId
| Enabled |  |  | Enabled
CreateUserId
CreateDateTime
LastChangeUserId
LastChangeDateTime
EmailId
ImageUrl
|  |  | role | user
|  |  | id | id
|  |  | name | name
|  |  | guard_name | email
|  |  | created_at | phone
|  |  | updated_at | email_verified_at
password
remember_token
status
created_at
updated_at

## Talend(ETL)
Talend will apply latest rules to the data and passon to the click house db
Need to decide which are all the data to be pushed, on what format
Clarifications
No of talend Service to be deployed, whether to be added in lambda or it will run separately outside?

## Dashboard
1. Apache Super Set will be used for this purpose, with option for intervention

## High level
Task list
Configuration Application | PHPlaravel | 2 | Full stack developers
Transformation Application | Java EE | 2 | Core java developers
Discovery and configuration editor changes | C#,
DB design and setup | Mohan, Kannan, Complere
Dashboarding | Complere system | TBD
Development of Intervention | Complere system
Moodle, Canvas, Blackboard | Shankar | 3
ML Development | Kannan
SIS (2 systems)
Infra setup, security | Compelre Systems
SalesforceV+ 1 CRM for tracking intervention | Compelre Systems
User Registers

## Clickhouse DB design and setup
DB design and setup | 4 weeks for initial design
Understanding SIS, LMS and CRM systems data elements required for the anaysis
Key metrics and summarization identifications
Key demesion identification
Identification of relationships
Tokenized columns to prortect PII
Data partitioning design
One DB for all
Backup and recovery of Clickhouse
Autoscaling of Clickhouse - Yandex clound?
Dashboard security - login (sso?)

## Dashboard and Intervention
UI Development and integration with Reveal.ai
Dashboard design concept
Dashboard HTML and angular development
Integrating with Security for login and data filters (row level filtering)
15 to 20 pages for intervention
Integration with Reveal.ai dashboard inside the Intevention UI
Deployment and Testing
Meta data integration for rules at row level. table level and user level
CRM Connectors or Local storage
- Salesforce case connector
- Salesforce case tracker
- Another crm case connector
- Another CRM case tracker

## Connectors and meta data discov
LMS Connector, API and Meta extract | 6 weeks
Canvas API - setup
Canvas meta data discovery
Canvas custom and plug-in fields
Canvas version support | [5 empty] | CANVAS |  | CLICKHOUSE
Moodle API - setup |  | cANVAS | API |  |  | F1 | STRING | FIRST NAME
Moodle custom and plugin fields data discovery |  | f1 | kn | First name | kn | F2 | STRING | LAST NAME
Moodle fields |  | f2 | jj | Last name | jj | FZ | STRING | FULL NAME
Moodle Version Support
Blackboard API - setup
Blackboard custom and plugin fields data discovery
Blackboard fields
Blackboard Version Support
SIS connector, API and Meta extract | 4 Weeks
Peoplesoft Data connector for education
Peoplesoft Metadata
Peoplesoft custom fields
Peoplesoft version support
,,, one miore SIS
Query Data - first time and incremental for SIS and LMS | 4 Weeks

## Configuration Application
Configuration UI |  | 12 weeks
New LMS, SIS and CRM connectors
Discovery process changes
Pivoting changes
Adding Additional configuration elemenets for PII, filters etc
Reporting Data integraty
Failure audits
Security audits |  | ??????
SSO (phase 2)
Realtime notifications
Discovery on Amazon Lamda
Basic UI Design | https://www.pixinvent.com/demo/frest-bootstrap-laravel-admin-dashboard-template/demo-1/dashboard/analytics
Schema Design | 2021-06-18
Installation of Laravel in server | 2021-06-21
UI Design In laravel | Depends on HTML Template Supply
Discovery process from the selected data instance
Installation of Laravel schema Crawler | 2021-06-23
Data Processing with Json | 2021-06-30
Data Audit | 2021-07-07
Table configuration | 2021-07-07
Uniqueness | 2021-07-07
Labels | 2021-07-07
Relationships | 2021-07-07
Pivot | 2021-07-07
Un-Pivot | 2021-07-07
Column Rules | 2021-07-15
Data Vlidation | 2021-07-15
Data Transformation | 2021-07-15
Data aggregation | 2021-07-15
Data object Types | 2021-07-15
Formula | ?????
Security Audit | ???

## Automation of ETL
ETL module - java
Meta data cache
Pivoting changes
Reporting Data integraty
Failure audits
Lamda coding for serverless ETL
Target write to S3
Insert, delete and updates in clickhouse
Performance enhancements

## API and Data Imports
Configuration UI
New LMS, SIS and CRM connectors
Discovery process changes
Pivoting changes
Adding Additional configuration elemenets for PII, filters etc
Reporting Data integraty
Failure audits
Security audits